## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Research | 1 | 2022-11-16 | Looking into what maze algorithm I'll do, and did the logic on paper on how I would implement it in code
Research | 2 | 2022-11-16 | Looked through some tutorials of some missing knowledge, like how to properly adjusting screen sizes, doing a custom skybox. I also was deciding whether to do it in 2D or 3D, and decided with 3D because I am more experienced with it, and the assignment seemed to be pushing more towards the 3D direction anyways
Implementing scene | 2 | 2022-11-17 | Started with making 3d objects and adjusting before jumping into the algorithm. So with the algorithm in mind, I made a cell that had 4 walls, which would form a grid, which would end up being the maze. Then, to make the maze, I would remove walls from some cells.
Implementing algorithm | 3 | 2022-11-20 | Jumped into making the randomized depth-first search, since I was the more familiar with it. It took some time to get the start going, since sometimes I thought I could use arrays, but then opted for hashsets instead. Or how I ended up using a keyvalue in some other places. Nonetheless, implementing the algorithm as I imagined it went well After getting the theory figured out, I implemented it
Debugging | 2 | 2022-11-20 | The sceen and prefab I made were buggy, so I had to adjust it according to the algorithm. When I wanted a specific wall to disappear, another wall would disappear. After some time, one of the bugs was that the grid was mirrors and translates wrong, so I adjusted it.
Debugging | 3 | 2022-11-21 | Algorithm was still buggy. So I had to look into why with the debugger, which took a lot of time. In the end, there was a couple of logic flaws that I fixed up. Such as missing to do the last edge-case, of what happens when the last cell needs to be calculated, I had thought it was calculated when it actually was not. Then there was some experimenting done with other edge-cases with > and >=, and so forth
Implementing last features | 1 | 2022-11-21 | Making sure that the input fields worked correctly such that only ints above 10 can be accepted. Linked all the buttons up. The resizing worked well for all 3 different mentioned sized
Implementing first person | 3 | 2022-11-21 | Wanted to make it that the player could use the maze, so now with WASD and camera movement, player can run around in the maze with the goal to touch a ball. Took longer than expected because there was some instansiating issues with the position | x
Implementing different colors | 1 | 2022-11-21 | Maze had different color variations, click on generate maze a couple of times and you'll see different themes | x
Polishing up | 1 | 2022-11-21 | Added comments and removed redundant code
Debugging | 3 | 2022-11-23 | Found a bug that ruins the algorithm if the button is pressed twice, so now the button is disabled until the allgorith is finished, so it can't be interupted
Final checks | 1 | 2022-11-23 | Making sure it all works well
Total amount of hours | 19